## task list
IKEA SL E-COMMERCE SITE
No | Release | Sprint | Epic | Process | Entered by | Task | Responsible | Due date | Completed on | Status
1 | 1 | 1 | Admin start | Admin login | Project Manager | User story 1 | Project Manager | 2020-07-20 | 2020-07-22 | done
2 | 1 | 1 | Admin start | Admin login | Project Manager | Review requirements | Business Analyst | 2020-07-20 | 2020-07-22 | done
3 | 1 | 1 | Admin start | Admin login | Project Manager | Design | UI/UX engineer | 2020-07-20 | 2020-07-22 | done
4 | 1 | 1 | Admin start | Admin login | Project Manager | Develop | Developer 1 | 2020-07-20 | 2020-07-22 | done
5 | 1 | 1 | Admin start | Admin login | Project Manager | Test | QA Engineer | 2020-07-20 | 2020-07-22 | done
6 | 1 | 1 | Home page | View product | Project Manager | User story 2 | Project Manager | 2020-07-22 | 2020-07-24 | done
7 | 1 | 1 | Home page | View product | Project Manager | Design | UI/UX engineer | 2020-07-22 | 2020-07-24 | done
8 | 1 | 1 | Home page | View product | Project Manager | Develop | Developer 1 | 2020-07-22 | 2020-07-24 | done
9 | 1 | 1 | Home page | View product | Project Manager | Test | QA Engineer | 2020-07-22 | 2020-07-24 | done
10 | 1 | 1 | Admin start | Admin signup | Project Manager | User srory 3 | Project Manager | 2020-07-24 | 2020-07-29 | done
11 | 1 | 1 | Admin start | Admin signup | Project Manager | Design | UI/UX engineer | 2020-07-24 | 2020-07-29 | done
12 | 1 | 1 | Admin start | Admin signup | Project Manager | Develop | Developer 1 | 2020-07-24 | 2020-07-29 | done
13 | 1 | 1 | Admin start | Admin signup | Project Manager | Test | QA Engineer | 2020-07-24 | 2020-07-29 | done
14 | 1 | 1 | Admin Dashboard | Admin Product area | Project Manager | User story 4 | Project Manager | 2020-07-29 | 2020-07-03 | done
15 | 1 | 1 | Admin Dashboard | Admin Product area | Project Manager | Review requirements | Business Analyst | 2020-07-29 | 2020-07-03 | done
16 | 1 | 1 | Admin Dashboard | Admin Product area | Project Manager | Design | UI/UX engineer | 2020-07-29 | 2020-07-03 | done
17 | 1 | 1 | Admin Dashboard | Admin Product area | Project Manager | Develop | Developer 1 | 2020-07-29 | 2020-07-03 | done
18 | 1 | 1 | Admin Dashboard | Admin Product area | Project Manager | Test | QA Engineer | 2020-07-29 | 2020-07-03 | done
19 | 1 | 1 | V e r I f y | I s s u e s | QA Engineer | Correct issues | Developer 1 | 2020-07-29 | 2020-07-03 | done
20 | 1 | 2 | Home page | Search product | Project Manager | User story 5 | Project Manager | 2020-07-03 | 2020-08-06 | done
21 | 1 | 2 | Home page | Search product | Project Manager | Design | UI/UX engineer | 2020-07-03 | 2020-08-06 | done
22 | 1 | 2 | Home page | Search product | Project Manager | Develop | Developer 2 | 2020-07-03 | 2020-08-06 | done
23 | 1 | 2 | Home page | Search product | Project Manager | Test | QA Engineer | 2020-07-03 | 2020-08-06 | done
24 | 1 | 2 | Home page | Add to cart | Project Manager | User story 6 | Project Manager | 2020-08-06 | 2020-08-10 | done
25 | 1 | 2 | Home page | Add to cart | Project Manager | Design | UI/UX engineer | 2020-08-06 | 2020-08-10 | done
26 | 1 | 2 | Home page | Add to cart | Project Manager | Develop | Developer 2 | 2020-08-06 | 2020-08-10 | done
27 | 1 | 2 | Home page | Add to cart | Project Manager | Test | QA Engineer | 2020-08-06 | 2020-08-10 | done
28 | 1 | 2 | Home page | IKEA Vission | Project Manager | User story 7 | Project Manager | 2020-08-10 | 2020-08-11 | done
2 | 1 | 2 | Home page | IKEA Vission | Project Manager | Review requirements | Business Analyst | 2020-08-10 | 2020-08-11 | done
30 | 1 | 2 | Home page | IKEA Vission | Project Manager | Design | UI/UX engineer | 2020-08-10 | 2020-08-11 | done
31 | 1 | 2 | Home page | IKEA Vission | Project Manager | Develop | Developer 2 | 2020-08-10 | 2020-08-11 | done
32 | 1 | 2 | Home page | IKEA Vission | Project Manager | Test | QA Engineer | 2020-08-10 | 2020-08-11 | done
33 | 1 | 2 | Home page | Help | Project Manager | User story 8 | Project Manager | 2020-08-11 |  | open
34 | 1 | 2 | Home page | Help | Project Manager | Review requirements | Business Analyst | 2020-08-11 |  | open
35 | 1 | 2 | Home page | Help | Project Manager | Design | UI/UX engineer | 2020-08-11 |  | open
36 | 1 | 2 | Home page | Help | Project Manager | develop | Developer 2 | 2020-08-11 |  | open
37 | 1 | 2 | Home page | Help | Project Manager | Test | QA Engineer | 2020-08-11 |  | open
38 | 2 | 2 | cart | remove cart items | Project Manager | user story 9 | Project Manager | 2020-08-12 | 2020-08-17 | done
39 | 2 | 2 | cart | remove cart items | Project Manager | Review requirements | Business Analyst | 2020-08-12 | 2020-08-17 | done
40 | 2 | 2 | cart | remove cart items | Project Manager | Design | UI/UX engineer | 2020-08-12 | 2020-08-17 | done
41 | 2 | 2 | cart | remove cart items | Project Manager | Develop | Developer 2 | 2020-08-12 | 2020-08-17 | done
42 | 2 | 2 | cart | remove cart items | Project Manager | Test | QA Engineer | 2020-08-12 | 2020-08-17 | done
43 | 2 | 2 | cart | continue shopping | Project Manager | user story 10 | Project Manager | 2020-08-17 | 2020-08-19 | done
44 | 2 | 2 | cart | continue shopping | Project Manager | design | UI/UX engineer | 2020-08-17 | 2020-08-19 | done
45 | 2 | 2 | cart | continue shopping | Project Manager | develop | Developer 2 | 2020-08-17 | 2020-08-19 | done
4 6 | 2 | 2 | cart | continue shopping | Project Manager | Test | QA Engineer | 2020-08-17 | 2020-08-19 | done
47 | 2 | 2 | cart | view check out | Project Manager | user story 11 | Project Manager | 2020-08-19 | 2020-08-21 | done
48 | 2 | 2 | cart | view check out | Project Manager | Design | UI/UX engineer | 2020-08-19 | 2020-08-21 | done
49 | 2 | 2 | cart | view check out | Project Manager | Develop | developer 2 | 2020-08-19 | 2020-08-21 | done
50 | 2 | 2 | cart | view check out | Project Manager | test | QA Engineer | 2020-08-19 | 2020-08-21 | done
51 | 2 | 2 | V e r I f y | I s s u e s | QA Engineer | Correct issues | developer 2 | 2020-08-19 | 2020-08-21 | done
52 | 2 | 3 | Admin Dashboard | Admin profile setting | Project Manager | user story 12 | Project Manager | 2020-08-21 | 2020-08-25 | done
53 | 2 | 3 | Admin Dashboard | Admin profile setting | Project Manager | Review requirements | Business Analyst | 2020-08-21 | 2020-08-25 | done
54 | 2 | 3 | Admin Dashboard | Admin profile setting | Project Manager | Design | UI/UX engineer | 2020-08-21 | 2020-08-25 | done
55 | 2 | 3 | Admin Dashboard | Admin profile setting | Project Manager | Develop | Developer 1 | 2020-08-21 | 2020-08-25 | done
56 | 2 | 3 | Admin Dashboard | Admin profile setting | Project Manager | Test | QA Engineer | 2020-08-21 | 2020-08-25 | done
57 | 2 | 3 | Admin Dashboard | Admin detals and image | Project Manager | User srtory 13 | Project Manager | 2020-08-25 | 2020-08-26 | done
58 | 2 | 3 | Admin Dashboard | Admin detals and image | Project Manager | Design | UI/UX engineer | 2020-08-25 | 2020-08-26 | done
59 | 2 | 3 | Admin Dashboard | Admin detals and image | Project Manager | Develop | developer 1 | 2020-08-25 | 2020-08-26 | done
60 | 2 | 3 | Admin Dashboard | Admin detals and image | Project Manager | Test | QA Engineer | 2020-08-25 | 2020-08-26 | done
61 | 2 | 3 | Admin Dashboard | Admin logout | Project Manager | User story 14 | Project Manager | 2020-08-26 | 2020-08-28 | done
62 | 2 | 3 | Admin Dashboard | Admin logout | Project Manager | Design | UI/UX engineer | 2020-08-26 | 2020-08-28 | done
63 | 2 | 3 | Admin Dashboard | Admin logout | Project Manager | Develop | developer 1 | 2020-08-26 | 2020-08-28 | done
64 | 2 | 3 | Admin Dashboard | Admin logout | Project Manager | Test | QA Engineer | 2020-08-26 | 2020-08-28 | done
65 | 2 | 3 | V e r I f y | I s s u e s | QA Engineer | Correct issues | Developer 1 | 2020-08-26 | 2020-08-28 | done
66 | 2 | 4 | Checkout page | product details | Project Manager | User story 15 | Project Manager | 2020-08-28 | 2020-09-03 | done
67 | 2 | 4 | Checkout page | product details | Project Manager | design | UI/UX engineer | 2020-08-28 | 2020-09-03 | done
68 | 2 | 4 | Checkout page | product details | Project Manager | develop | developer 2 | 2020-08-28 | 2020-09-03 | done
69 | 2 | 4 | Checkout page | product details | Project Manager | Test | QA Engineer | 2020-08-28 | 2020-09-03 | done
70 | 2 | 4 | Home page | front image | Project Manager | User story 16 | Project Manager | 2020-09-03 | 2020-09-04 | done
71 | 2 | 4 | Home page | front image | Project Manager | design | UI/UX engineer | 2020-09-03 | 2020-09-04 | done
72 | 2 | 4 | Home page | front image | Project Manager | Develop | developer 2 | 2020-09-03 | 2020-09-04 | done
73 | 2 | 4 | Home page | front image | Project Manager | Test | QA Engineer | 2020-09-03 | 2020-09-04 | done
74 | 3 | 4 | Checkout page | Payment details | Project Manager | User story 17 | Project Manager | 2020-09-04 | 2020-09-10 | done
75 | 3 | 4 | Checkout page | Payment details | Project Manager | design | UI/UX engineer | 2020-09-04 |  | open
76 | 3 | 4 | Checkout page | Payment details | Project Manager | Review requirements | Business Analyst | 2020-09-04 |  | open
77 | 3 | 4 | Checkout page | Payment details | Project Manager | develop | developer 2 | 2020-09-04 |  | open
78 | 3 | 4 | Checkout page | Payment details | Project Manager | Test | QA Engineer | 2020-09-04 |  | open
79 | 3 | 4 | Home page | Contact details | Project Manager | User story 18 | Project Manager | 2020-09-10 |  | open
80 | 3 | 4 | Home page | Contact details | Project Manager | design | UI/UX engineer | 2020-09-10 |  | open
81 | 3 | 4 | Home page | Contact details | Project Manager | develop | developer 2 | 2020-09-10 |  | open
82 | 3 | 4 | Home page | Contact details | Project Manager | Test | QA Engineer | 2020-09-10 |  | open
83 | 3 | 4 | V e r I f y | I s s u e s | QA Engineer | Correct issues | Developer | 2020-09-10 |  | open
84 | 3 | 5 | Admin Dashboard | Admin orders | Project Manager | User story 19 | Project Manager | 2020-09-14 | 2020-09-17 | done
85 | 3 | 5 | Admin Dashboard | Admin orders | Project Manager | Review requirements | Business Analyst | 2020-09-14 | 2020-09-17 | done
86 | 3 | 5 | Admin Dashboard | Admin orders | Project Manager | design | UI/UX engineer | 2020-09-14 | 2020-09-17 | done
87 | 3 | 5 | Admin Dashboard | Admin orders | Project Manager | develop | developer 1 | 2020-09-14 | 2020-09-17 | done
88 | 3 | 5 | Admin Dashboard | Admin orders | Project Manager | Test | QA Engineer | 2020-09-14 | 2020-09-17 | done
89 | 3 | 5 | Admin Dashboard | Overview | Project Manager | User story 20 | Project Manager | 2020-09-17 | 2020-09-22 | done
90 | 3 | 5 | Admin Dashboard | Overview | Project Manager | Review requirements | Business Analyst | 2020-09-17 | 2020-09-22 | done
91 | 3 | 5 | Admin Dashboard | Overview | Project Manager | Design | UI/UX engineer | 2020-09-17 | 2020-09-22 | done
92 | 3 | 5 | Admin Dashboard | Overview | Project Manager | develop | developer 1 | 2020-09-17 | 2020-09-22 | done
92 | 3 | 5 | Admin Dashboard | Overview | Project Manager | Test | QA Engineer | 2020-09-17 | 2020-09-22 | done
94 | 3 | 5 | Checkout page | product image | Project Manager | User story 21 | Project Manager | 2020-09-22 | 2020-09-23 | done
95 | 3 | 5 | Checkout page | product image | Project Manager | design | UI/UX engineer | 2020-09-22 | 2020-09-23 | done
96 | 3 | 5 | Checkout page | product image | Project Manager | develop | developer 2 | 2020-09-22 | 2020-09-23 | done
97 | 3 | 5 | Checkout page | product image | Project Manager | Test | QA Engineer | 2020-09-22 | 2020-09-23 | done
98 | 3 | 5 | Checkout page | order details | Project Manager | User story 22 | Project Manager | 2020-09-23 |  | in work
99 | 3 | 5 | Checkout page | order details | Project Manager | design | UI/UX engineer | 2020-09-23 |  | in work
100 | 3 | 5 | Checkout page | order details | Project Manager | develop | developer 2 | 2020-09-23 |  | in work
101 | 3 | 5 | Checkout page | order details | Project Manager | Test | QA Engineer | 2020-09-23 |  | in work
102 | 3 | 5 | Home page | IKEA LOGO | Project Manager | User story 23 | Project Manager | 2020-09-24 | 2020-09-25 | done
103 | 3 | 5 | Home page | IKEA LOGO | Project Manager | Design | UI/UX engineer | 2020-09-24 | 2020-09-25 | done
194 | 3 | 5 | Home page | IKEA LOGO | Project Manager | develop | developer 2 | 2020-09-24 | 2020-09-25 | done
105 | 3 | 5 | Home page | IKEA LOGO | Project Manager | Test | QA Engineer | 2020-09-24 | 2020-09-25 | done
106 | 3 | 5 | V e r I f y | I s s u e s | QA Engineer | Correct issues | developer 1 and 2 | 2020-09-24 | 2020-09-25 | done

## status
open
in work
done